## SAHARA Project Log
SAHARA — Smart AI Healthcare Assistance & Rapid Aid
Buildables AI/ML Fellowship 2025 ¦ Author: Ayesha ¦ Period: 29 March – 18 April 2026 ¦ Total: 4 Weeks
Project execution log covering all tasks from 29 March to 18 April 2026 across 4 development phases.
TASK LOG (29 March – 18 April 2026)
Week | Date | Task / Deliverable | Category | Status | Progress | Notes
W1 | 29–30 Mar | Exploratory Data Analysis (EDA) — RF + ANN | Data Science | Done ✓ | 100% | Both models analyzed
W1 | 29–30 Mar | Feature Engineering — Binary symptoms (RF) | Data Science | Done ✓ | 100% | Binary encoding done
W1 | 29–30 Mar | Feature Engineering — TF-IDF 500 (ANN) | Data Science | Done ✓ | 100% | TF-IDF vectorized
W1 | 31 Mar–1 Apr | Random Forest training (~98% accuracy) | ML Training | Done ✓ | 100% | 98% acc achieved
W1 | 1–2 Apr | ANN training — 4 layers (~86% accuracy) | ML Training | Done ✓ | 100% | 86% acc achieved
W1 | 2–3 Apr | Model evaluation — confusion matrix, F1 | ML Evaluation | Done ✓ | 100% | F1 scores logged
W2 | 4 Apr | FastAPI backend setup + CORS | Backend | Done ✓ | 100% | Endpoints configured
W2 | 4–5 Apr | Model loader service (RF + ANN) | Backend | Done ✓ | 100% | Both models loaded
W2 | 5–6 Apr | /predict/step1 endpoint (RF → category) | Backend | Done ✓ | 100% | Category prediction live
W2 | 6–7 Apr | /predict/step2 endpoint (ANN → top3) | Backend | Done ✓ | 100% | Top 3 diseases returned
W2 | 7–8 Apr | Groq LLaMA NLP integration | NLP | Done ✓ | 100% | Symptom parser live
W2 | 7–8 Apr | NLP utils — symptom normalization | NLP | Done ✓ | 100% | Text cleaned & mapped
W2 | 8 Apr | API testing with Swagger /docs | Testing | Done ✓ | 100% | All endpoints tested
W3 | 6–7 Apr | React + Vite + Tailwind CSS setup | Frontend | Done ✓ | 100% | Project scaffolded
W3 | 7–8 Apr | Firebase Auth — Google Sign In | Frontend | Done ✓ | 100% | Auth integrated
W3 | 8–10 Apr | AI Check page — 2-step symptom checker | Frontend | Done ✓ | 100% | Step1 + Step2 UI done
W3 | 9–10 Apr | Doctors page — 39 local doctors | Frontend | Done ✓ | 100% | Cards + filter ready
W3 | 9–10 Apr | Hospitals page — 34 hospitals Attock | Frontend | Done ✓ | 100% | Map + list view done
W3 | 10–11 Apr | Emergency page — GPS + hospital finder | Frontend | Done ✓ | 100% | GPS location working
W3 | 10–12 Apr | Home, About, Navbar, Footer, Chatbot | Frontend | Done ✓ | 100% | All pages complete
W4 | 13–14 Apr | GitHub repository — clean push | Deployment | Done ✓ | 100% | Code finalized
W4 | 14 Apr | HuggingFace — model files upload | Deployment | Done ✓ | 100% | RF + ANN models live
W4 | 14 Apr | Vercel — frontend deployment | Deployment | Done ✓ | 100% | Live URL active
W4 | 15–16 Apr | HuggingFace — backend deployment | Deployment | Done ✓ | 100% | FastAPI live
W4 | 15 Apr | Firebase authorized domains update | Configuration | Done ✓ | 100% | Auth prod-ready
W4 | 16 Apr | README — professional documentation | Documentation | Done ✓ | 100% | Full setup guide
W4 | 16–17 Apr | Presentation slides (Canva) | Presentation | Done ✓ | 100% | Professional deck
W4 | 17 Apr | Final report (PDF) | Documentation | Done ✓ | 100% | Methodology + results
W4 | 17 Apr | Medium article | Documentation | Done ✓ | 100% | Published online
W4 | 17 Apr | Gantt chart (XLS) | Documentation | Done ✓ | 100% | 4-week timeline
W4 | 18 Apr | Demo video recording | Presentation | Done ✓ | 100% | All features shown
W4 | 18 Apr | Final submission & interview prep | Submission | Done ✓ | 100% | Submitted on time