## SAHARA Gantt Chart
SAHARA — Smart AI Healthcare Assistance & Rapid Aid ¦ Project Execution Plan
Buildables AI/ML Fellowship 2025 ¦ Author: Ayesha ¦ Duration: 23 March – 18 April 2026 ¦ Total: 4 Weeks
Legend: |  |  |  | Completed | In Progress | Planned
Task / Phase | Owner | Status | Progress | 23 Mon | 24 Tue | 25 Wed | 26 Thu | 27 Fri | 28 Sat | 29 Sun | 30 Mon | 31 Tue | 01 Wed | 02 Thu | 03 Fri | 04 Sat | 05 Sun | 06 Mon | 07 Tue | 08 Wed | 09 Thu | 10 Fri | 11 Sat | 12 Sun | 13 Mon | 14 Tue | 15 Wed | 16 Thu | 17 Fri | 18 Sat
WEEK 1 — Data & Model Development
Define problem statement & objectives | Ayesha | Done | 100%
Dataset collection (Kaggle + HuggingFace) | Ayesha | Done | 100%
GitHub repo setup & project structure | Ayesha | Done | 100%
Data cleaning — RF dataset (41 diseases) | Ayesha | Done | 100%
Data cleaning — ANN dataset (22 diseases) | Ayesha | Done | 100%
Exploratory Data Analysis (EDA) — RF + ANN | Ayesha | Done | 100%
Feature Engineering — Binary symptoms (RF) | Ayesha | Done | 100%
Feature Engineering — TF-IDF 500 (ANN) | Ayesha | Done | 100%
Random Forest training (~98% accuracy) | Ayesha | Done | 100%
ANN training — 4 layers (~86% accuracy) | Ayesha | Done | 100%
Model evaluation — confusion matrix, F1 | Ayesha | Done | 100%
WEEK 2 — Backend & API Development
FastAPI backend setup + CORS | Ayesha | Done | 100%
Model loader service (RF + ANN) | Ayesha | Done | 100%
/predict/step1 endpoint (RF → category) | Ayesha | Done | 100%
/predict/step2 endpoint (ANN → top3) | Ayesha | Done | 100%
Groq LLaMA NLP integration | Ayesha | Done | 100%
NLP utils — symptom normalization | Ayesha | Done | 100%
API testing with Swagger /docs | Ayesha | Done | 100%
WEEK 3 — Frontend Development
React + Vite + Tailwind CSS setup | Ayesha | Done | 100%
Firebase Auth — Google Sign In | Ayesha | Done | 100%
AI Check page — 2-step symptom checker | Ayesha | Done | 100%
Doctors page — 39 local doctors | Ayesha | Done | 100%
Hospitals page — 34 hospitals Attock | Ayesha | Done | 100%
Emergency page — GPS + hospital finder | Ayesha | Done | 100%
Home, About, Navbar, Footer, Chatbot | Ayesha | Done | 100%
WEEK 4 — Deployment & Documentation
GitHub repository — clean push | Ayesha | Done | 100%
HuggingFace — model files upload | Ayesha | Done | 100%
Vercel — frontend deployment | Ayesha | Done | 100%
hugging face — backend deployment | Ayesha | Done | 100%
Firebase authorized domains update | Ayesha | Done | 100%
README — professional documentation | Ayesha | Done | 100%
Presentation slides (Canva) | Ayesha | Done | 100%
Final report (PDF) | Ayesha | Done | 100%
Medium article | Ayesha | Done | 100%
Gantt chart (XLS) | Ayesha | Done | 100%
Demo video recording | Ayesha | Done | 100%
Final submission & interview prep | Ayesha | Done | 100%
SAHARA Project Summary ¦ GitHub: github.com/Ayesha0000000 ¦ Live: sahara-smart-ai-healthcare-assistan.vercel.app ¦ HuggingFace: huggingface.co/Ayesh104/SAHARA-Model